## Sheet4
Requirement ID | Story ID | Technical Requirement | Priority | Delivery Phase | Title | Work item type | state | ADO Import Status | Epic | Feature | Story Swimlane Step / Component | Product Variation(s) | Source Module
CIP-CE-003 | CIP-PA-015 | The CIP platform shall implement : BioBERT PRIOR_AUTH_APPEALS model group — Prior Auth, Appeal, Peer-to-Peer, CDI Query Prior Authorization Prior Authorization document types. | P1 | Phase 1 | BioBERT Prior Authorization Document Model | User Story | New | Pending | Classification | PA Document Classification | 4 - Extract & Classify; 6 - Confidence Score | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Classify & Extract
CIP-CE-003 | CIP-PA-016 | The CIP platform shall implement : Rules engine extraction — Method 2, prior auth and appeal Prior Authorization Prior Authorization document types with clinical indication parsing. CIP shall support Rules engine extraction, including Method 2, prior auth and appeal Prior Authorization Prior Authorization document types with clinical indication parsing, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | Rules-Based Prior Authorization Extraction | User Story | New | Pending | Classification | PA Data Extraction | 4 - Extract & Classify | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Classify & Extract
CIP-CE-003 | CIP-PA-019 | The CIP platform shall implement : Confidence score calculation per extracted field — field-level confidence, GREEN AMBER RED classification. | P1 | Phase 1 | Field-Level Extraction Confidence Scoring | User Story | New | Pending | Classification | Extraction Confidence & STP | 6 - Confidence Score | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Classify & Extract
CIP-CE-006 | CIP-PA-020 | The CIP platform shall implement : Composite STP gate score — min(field_scores) x criteria_met_pct x domain_risk_factor. | P1 | Phase 1 | Composite STP Gate Scoring | User Story | New | Pending | Criteria & Clinical Evaluation | Extraction Confidence & STP | 6 - Confidence Score | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Classify & Extract
CIP-CE-010 | CIP-PA-021 | The CIP platform shall implement : STP gate logic — threshold comparison against dim_document_types stp_threshold, mandatory field presence check. | P1 | Phase 1 | STP Gate Validation Logic | User Story | New | Pending | Core Platform Capabilities | Extraction Confidence & STP | 6 - Confidence Score | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Classify & Extract
CIP-CG-004 | CIP-PA-032 | The CIP platform shall implement : InterQual 2026 integration — per-criterion evaluation for Prior Auth and applicable clinical domains. CIP shall support InterQual 2026 integration, including per-criterion evaluation for Prior Auth and applicable clinical domains, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | InterQual 2026 Integration | User Story | New | Pending | API & Integration | Clinical Guideline Integration | 5 - Clinical Guidelines Validation | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Clinical guidelines
CIP-CG-004 | CIP-PA-034 | The CIP platform shall implement : NCCN integration — oncology and specialty criteria evaluation. CIP shall support NCCN integration, including oncology and specialty criteria evaluation, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | NCCN Integration | User Story | New | Pending | API & Integration | Clinical Guideline Integration | 5 - Clinical Guidelines Validation | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Clinical guidelines
CIP-WIP-002 | CIP-PA-057 | The CIP platform shall implement : Extraction failure compensating action — retry up to 3 times, then FAILED with structured reason. CIP shall support Extraction failure compensating action, including retry up to 3 times, then FAILED with structured reason, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | Extraction Failure Compensating Action | User Story | New | Pending | Extraction & OCR | Extraction Error Handling | 4 - Extract & Classify | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | WIP Pipeline
CIP-WIP-001 | CIP-PA-061 | The CIP platform shall implement : Delivery failure compensating action — retry via alternate channel after 3 exhausted attempts. | P1 | Phase 1 | Delivery Failure Compensating Action | User Story | New | Pending | Communication & Delivery | Delivery Retry & Recovery | 23 - Deliver to Client | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | WIP Pipeline
CIP-WIP-001 | CIP-PA-062 | The CIP platform shall implement : SagaMonitor polling loop — 30-second interval background task. | P1 | Phase 1 | SagaMonitor Polling Loop | User Story | New | Pending | Communication & Delivery | Saga Orchestration & Monitoring | 16 - Edit & Submit | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | WIP Pipeline
CIP-WIP-007 | CIP-PA-064 | The CIP platform shall implement : OutboxRelay background process — SELECT FOR UPDATE SKIP LOCKED polling. CIP shall provide reliable publication of business events using transactional event capture and resilient asynchronous delivery, ensuring committed business transactions are not lost to downstream workflows due to event-publishing failures | P0 | Phase 1 | OutboxRelay Background Process | User Story | New | Pending | Workflow & Event Orchestration | Outbox Event Processing | WIP Pipeline | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | WIP Pipeline
CIP-WIP-007 | CIP-PA-065 | The CIP platform shall implement : OutboxRelay Kafka publish with at-least-once delivery semantics. CIP shall support OutboxRelay Kafka publish with at-least-once delivery semantics using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | OutboxRelay Kafka Publish with At-least-once Delivery Semantics | User Story | New | Pending | Workflow & Event Orchestration | Outbox Event Processing | WIP Pipeline | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | WIP Pipeline
CIP-WIP-007 | CIP-PA-066 | The CIP platform shall implement : Outbox health endpoint — GET /health/outbox with pending published failed counts. The CIP platform shall expose an operational health endpoint for the transactional outbox that reports event backlog and processing health, including pending, successfully published, failed, retrying, and aged events, enabling automated monitoring and alerting of Kafka event-publication failures. | P1 | Phase 1 | Outbox Health Endpoint | User Story | New | Pending | Workflow & Event Orchestration | Outbox Event Processing | WIP Pipeline | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | WIP Pipeline
CIP-WIP-008 | CIP-PA-067 | The CIP platform shall implement : Saga state engineering dashboard — per-state transaction counts, timeout breach rate. CIP shall support Saga state engineering dashboard, including per-state transaction counts, timeout breach rate, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | Saga State Engineering Dashboard | User Story | New | Pending | Workflow & Event Orchestration | Saga Orchestration & Monitoring | WIP Pipeline | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | WIP Pipeline
CIP-CIOS-018 | CIP-PA-122 | The CIP platform shall implement : AI output PHI scanner — regex pattern check on AI responses before display, suppressed and incident logged if PHI detected. As a security and privacy administrator, I want CIOS to inspect AI-generated outputs for sensitive information and evaluate the detected information against the user's authorization, workflow purpose and output-channel policy before release, so that unauthorized or unnecessary PHI is redacted or suppressed and potential privacy violations are captured for investigation | P1 | Phase 1 | AI Output PHI Scanner | User Story | New | Pending | Security, Privacy & Access | AI Output Protection | 15 - Review & Validate | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | CIOS
CIP-VF-004 | CIP-PA-134 | The CIP platform shall implement : Two-step CoT letter drafting — Step 1 reasoning chain generates clinical rationale, Step 2 generates letter from reasoning chain. As an authorized Prior Authorization (or other process flows) reviewer, I want CIOS to generate determination communications from a structured, evidence-grounded and reviewer-validated clinical rationale so that adverse and partially adverse communications accurately reflect the actual basis for the determination without introducing unsupported clinical conclusions | P1 | Phase 1 | Two-step CoT Letter Drafting | User Story | New | Pending | Communication & Delivery | Validation & Exception Handling | 4a - Validation Decision | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Validation -- Failure
CIP-VF-004 | CIP-PA-137 | The CIP platform shall implement : Reflection revision loop — if issues found, one revision pass executed before presenting letter to processor. As a Prior Authorization processor, I want CIOS to automatically correct eligible issues identified during draft communication validation and revalidate the corrected communication before presenting it to me so that routine quality issues are resolved without creating uncontrolled AI revision loops or allowing unresolved high-risk issues to progress | P1 | Phase 1 | Reflection Revision Loop | User Story | New | Pending | Communication & Delivery | Validation & Exception Handling | 4a - Validation Decision | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Validation -- Failure
CIP-VF-004 | CIP-PA-139 | The CIP platform shall implement : Regulatory template selection — by Prior Authorization document type and client, appeal window 60 or 180 days per dim_clients. | P1 | Phase 1 | Regulatory Template Selection | User Story | New | Pending | Communication & Delivery | Validation & Exception Handling | 4a - Validation Decision | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Validation -- Failure
CIP-VF-002 | CIP-PA-145 | The CIP platform shall implement : comm_gate_applicable enforcement — gate applies to PRIOR_AUTH and APPEAL Prior Authorization Prior Authorization document types only per dim_document_types.As a clinical operations and compliance administrator, I want CIP to determine whether communication generation, validation and human confirmation controls apply to a transaction based on its workflow, determination and applicable client/regulatory policy so that communication controls are enforced only where required and cannot be inadvertently omitted from workflows where they are mandatory | P1 | Phase 1 | Comm_gate_applicable Enforcement | User Story | New | Pending | Classification | Validation & Exception Handling | 4 - Extract & Classify | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Validation -- Failure
CIP-INF-012 | CIP-PA-271 | The CIP platform shall implement : PostgreSQL row-level security — all wip_db Zone 2 tables have RLS enforced at engine level. CIP shall enforce row-level data access controls to ensure users and application services can access only the data they are explicitly authorized to view or process, supporting secure data isolation and least-privilege access. | P0 | Phase 1 | PostgreSQL Row-level Security | User Story | New | Pending | Core Platform Capabilities | Database Infrastructure & Security | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-DSEC-004 | CIP-PA-272 | The CIP platform shall implement : PHI zone classification — Zone 1 in motion TLS 1.3, Zone 2 at rest AES-256, Zone 3 operational metadata no PHI, Zone 4 aggregated analytics no PHI. CIP shall implement a governed data protection framework that classifies data based on sensitivity and usage, applies appropriate security controls for data in transit and at rest, and ensures PHI is excluded from operational metadata and aggregated analytics where not required. | P0 | Phase 1 | PHI Zone Classification | User Story | New | Pending | Security, Privacy & Access | Transport Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-004 | CIP-PA-273 | The CIP platform shall implement : Zone 2 AES-256 Azure Blob Storage — SSE with customer-managed key from Azure Key Vault per client VPC. CIP shall protect sensitive and PHI-containing data at rest using strong encryption, securely managed encryption keys, and appropriate client-level data isolation controls. | P0 | Phase 1 | Zone 2 AES-256 Azure Blob Storage | User Story | New | Pending | Security, Privacy & Access | Encryption at Rest | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-004 | CIP-PA-274 | The CIP platform shall implement : Zone 2 wip_db column encryption — pgcrypto pgp_sym_encrypt for highest-sensitivity fields member_dob_enc member_addr_enc. CIP shall provide enhanced protection for highly sensitive data elements through field-level encryption and governed access controls, ensuring protected information remains secure both at rest and during authorized use. | P0 | Phase 1 | Zone 2 Wip_db Column Encryption | User Story | New | Pending | Security, Privacy & Access | Data Protection & Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-005 | CIP-PA-275 | The CIP platform shall implement : Zone 3 PHI exclusion enforcement — Kafka producer code structural allowlist, no PHI in any Kafka topic. CIP shall enforce PHI-minimization controls for operational event and messaging data, ensuring only explicitly approved non-PHI data elements are published to shared event-processing services. | P0 | Phase 1 | Zone 3 PHI Exclusion Enforcement | User Story | New | Pending | Security, Privacy & Access | Data Protection & Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-005 | CIP-PA-276 | The CIP platform shall implement : Zone 4 structural PHI-free guarantee — as_db consumer groups write aggregates only, no raw clinical fields. CIP shall ensure analytical data products contain only approved aggregated or de-identified information, preventing raw clinical or PHI data elements from being introduced where they are not required | P0 | Phase 1 | Zone 4 Structural PHI-free Guarantee | User Story | New | Pending | Security, Privacy & Access | Data Protection & Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-001 | CIP-PA-277 | The CIP platform shall implement : TLS 1.3 enforcement — TLS 1.2 and below rejected at NGINX Ingress, ssl_protocols TLSv1.3 only. CIP shall enforce current approved secure communication protocols for data in transit, rejecting connections that use deprecated or non-compliant encryption protocols. | P0 | Phase 1 | TLS 1.3 Enforcement | User Story | New | Pending | Communication & Delivery | Transport Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-005 | CIP-PA-279 | The CIP platform shall implement : JWT authentication middleware — 15-minute expiry, validated on every API request. CIP shall enforce secure, token-based authentication for all API requests, validating user or service identity and authorization using time-limited credentials in accordance with defined security policies. | P0 | Phase 1 | JWT Authentication Middleware | User Story | New | Pending | Security, Privacy & Access | Identity & Access Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-006 | CIP-PA-281 | The CIP platform shall implement : Azure Key Vault integration — all credentials, API keys, JWT signing keys, PHI encryption keys, rotation schedules. CIP shall provide centralized and secure management of credentials, encryption keys, signing keys, and other application secrets, including controlled access, lifecycle management, and automated key and secret rotation in accordance with defined security policies. | P0 | Phase 1 | Azure Key Vault Integration | User Story | New | Pending | Security, Privacy & Access | Identity & Access Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-006 | CIP-PA-283 | The CIP platform shall implement : SHA-256 implementation — Python hashlib standard library, streaming for large documents, FIPS 140-2 compliant. CIP shall use approved cryptographic integrity controls to generate and verify tamper-evident fingerprints for source documents and applicable derived artifacts, supporting scalable processing, evidence provenance, and chain-of-custody requirements in accordance with applicable security standards. | P0 | Phase 1 | SHA-256 Implementation | User Story | New | Pending | Security, Privacy & Access | Data Integrity | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-DSEC-006 | CIP-PA-284 | The CIP platform shall implement : AES-256 implementation — Azure SSE for blob, pgcrypto for database columns, TLS 1.3 AES-256-GCM cipher for transit. CIP shall protect PHI and other sensitive information using approved cryptographic controls for data at rest and in transit, with additional field-level protection applied to designated high-sensitivity data elements and encryption keys securely managed throughout their lifecycle. | P0 | Phase 1 | AES-256 Implementation | User Story | New | Pending | Security, Privacy & Access | Transport Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-EDA-002 | CIP-PA-285 | The CIP platform shall implement : Kafka cluster provisioning — dedicated per client VPC, replication factor 3 across availability zones. CIP shall provide a highly available and resilient event-processing infrastructure with appropriate tenant isolation, redundancy, fault tolerance, and recovery controls to ensure reliable processing of business events without unauthorized cross-client data exposure | P0 | Phase 1 | Kafka Cluster Provisioning | User Story | New | Pending | Reliability, Performance & Operations | Kafka Infrastructure | Event-Driven Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Event Driven Architecture
CIP-EDA-003 | CIP-PA-286 | The CIP platform shall implement : SASL/SCRAM producer authentication within VPC — per-service credentials, no shared producer credentials. CIP shall enforce unique service identities and least-privilege access controls for event publishing and consumption, ensuring each application service can access only authorized event channels and that shared service credentials are prohibited. | P0 | Phase 1 | SASL/SCRAM Producer Authentication Within VPC | User Story | New | Pending | Workflow & Event Orchestration | Event & Messaging Infrastructure | Event-Driven Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Event Driven Architecture
CIP-EDA-003 | CIP-PA-287 | The CIP platform shall implement : Clinical pipeline topic creation — 16 topics T01-T16 with retention and replication configuration. CIP shall provide governed event channels for clinical and operational workflows, with standardized event schemas, versioning, security, retention, reliability, and replay controls to support resilient communication between platform services and downstream consumers. | P0 | Phase 1 | Clinical Pipeline Topic Creation | User Story | New | Pending | Workflow & Event Orchestration | Event & Messaging Infrastructure | Event-Driven Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Event Driven Architecture
CIP-EDA-003 | CIP-PA-288 | The CIP platform shall implement : Topic retention configuration — 90 days standard, indefinite chain.custody.entry. Event Retention : CIP shall apply governed retention policies to business events based on their operational, recovery, replay, and reconciliation requirements, with retention periods configurable by event classification and applicable policy Chain of Custody : CIP shall preserve material chain-of-custody and compliance evidence in a durable, tamper-resistant repository for the retention period required by applicable regulatory, contractual, and organizational policies | P0 | Phase 1 | Topic Retention Configuration | User Story | New | Pending | Workflow & Event Orchestration | Event & Messaging Infrastructure | Event-Driven Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Event Driven Architecture
CIP-EDA-004 | CIP-PA-289 | The CIP platform shall implement : Consumer group offset management — manual commit, at-least-once semantics, processed_events deduplication. CIP shall provide reliable and idempotent processing of business events through controlled acknowledgment, duplicate detection, retry and exception handling, and reconciliation mechanisms, ensuring processing failures do not result in lost events or duplicate business outcomes | P0 | Phase 1 | Consumer Group Offset Management | User Story | New | Pending | Workflow & Event Orchestration | Event & Messaging Infrastructure | Event-Driven Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Event Driven Architecture
CIP-EDA-004 | CIP-PA-292 | The CIP platform shall implement : Kafka consumer lag monitoring — Prometheus scrape, alerting thresholds per consumer group. CIP shall monitor the health and timeliness of event-processing services, including processing backlog, event age, throughput, latency, failures, retries, and exception volumes, with alerting thresholds aligned to the business criticality and service-level objectives of each downstream process. | P0 | Phase 1 | Kafka Consumer Lag Monitoring | User Story | New | Pending | Workflow & Event Orchestration | Kafka Monitoring | Event-Driven Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Event Driven Architecture
CIP-EDA-004 | CIP-PA-293 | The CIP platform shall implement : Topic-level ACL enforcement — per-producer topic permissions, prevents cross-service event injection. CIP shall enforce least-privilege authorization for business-event publishing and consumption, ensuring application services can access only approved event types and preventing unauthorized or cross-service event injection | P0 | Phase 1 | Topic-level ACL Enforcement | User Story | New | Pending | Workflow & Event Orchestration | Event & Messaging Infrastructure | Event-Driven Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Event Driven Architecture
CIP-INF-008 | CIP-PA-294 | The CIP platform shall implement : Terraform per-client VPC module — parameterised per payer, all resources provisioned in one terraform apply. CIP shall support automated, repeatable, and governed provisioning of client environments using approved infrastructure configurations, ensuring consistent security controls, appropriate tenant isolation, configuration traceability, and scalable client onboarding. | P0 | Phase 1 | Terraform Per-client VPC Module | User Story | New | Pending | Configuration & Administration | Deployment & Environment Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-INF-016 | CIP-PA-298 | The CIP platform shall implement : Staging deployment pipeline — post-merge automated deployment with integration test gate. CIP shall provide an automated non-production deployment and validation process that verifies integrated platform functionality, security, data and event compatibility, and applicable regression requirements before changes are eligible for production promotion | P0 | Phase 1 | Staging Deployment Pipeline | User Story | New | Pending | Security, Privacy & Access | Deployment & Environment Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-INF-015 | CIP-PA-300 | The CIP platform shall implement : Prometheus metrics instrumentation — all AKS pods, custom metrics for Kafka lag, SLA compliance, extraction confidence. CIP shall provide comprehensive observability across infrastructure, application services, integrations, event processing, and critical operational workflows, capturing standardized health, performance, availability, latency, error, and processing-freshness metrics to support proactive monitoring and alerting. | P0 | Phase 1 | Prometheus Metrics Instrumentation | User Story | New | Pending | Reliability, Performance & Operations | Platform Monitoring & Scaling | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-INF-016 | CIP-PA-303 | The CIP platform shall implement : Playwright E2E test suite — portal authentication, dashboard rendering, access control enforcement. CIP shall provide automated end-to-end validation of critical user and business workflows, including authentication, authorized functionality, data presentation, and tenant- and role-based access controls, preventing releases from progressing when critical workflow or security validations fai | P0 | Phase 1 | Playwright E2E Test Suite | User Story | New | Pending | Security, Privacy & Access | Deployment & Environment Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-INF-015 | CIP-PA-305 | The CIP platform shall implement : Azure Monitor and HPA — custom Kafka lag metric, HPA scales pods 2-10 on CPU > 70% or lag > 500. CIP shall dynamically scale application and processing capacity based on workload demand, processing backlog, service performance, and resource utilization to maintain defined availability, throughput, and processing-time objectives while optimizing infrastructure utilization | P0 | Phase 1 | Azure Monitor and HPA | User Story | New | Pending | Reliability, Performance & Operations | Platform Monitoring & Scaling | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-INF-006 | CIP-PA-306 | The CIP platform shall implement : Reject letter template library — by Prior Authorization document type, rejection reason, and state-specific regulatory requirements. CIP shall maintain a governed communication template library that supports selection of the appropriate approved template based on communication type, transaction and determination context, client and plan configuration, jurisdiction, language, and applicable regulatory or contractual requirements CIP shall support governed adverse-determination communication templates that incorporate applicable reason, regulatory, appeal-rights, and case-specific content requirements while maintaining version and approval traceability | P0 | Phase 1 | Reject Letter Template Library | User Story | New | Pending | Communication & Delivery | Platform Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-INF-006 | CIP-PA-307 | The CIP platform shall implement : State-specific regulatory template selection logic — jurisdiction mapping per payer client. CIP shall determine applicable communication requirements and approved template versions using governed, effective-dated policies based on jurisdiction, client, line of business, plan, transaction and determination context, and other applicable regulatory or contractual attributes | P0 | Phase 1 | State-specific Regulatory Template Selection Logic | User Story | New | Pending | Communication & Delivery | Platform Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-INF-006 | CIP-PA-308 | The CIP platform shall implement : Reject letter generation — local vLLM within VPC, administrative notice content. CIP shall generate case-specific administrative notices using validated transaction information, governed reason codes, applicable communication policies, and approved templates, with AI-assisted narrative generation used only where appropriate and subject to defined content validation and approval controls. | P0 | Phase 1 | Reject Letter Generation | User Story | New | Pending | Communication & Delivery | Deployment & Environment Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Infrastructure
CIP-APPSEC-010 | CIP-PA-316 | The CIP platform shall implement : AI output PHI scanner — regex pattern check on model responses before display, suppressed and incident logged if PHI detected. CIP shall validate AI-generated outputs against capability-specific data protection and disclosure policies before the output is displayed, transmitted, stored, or used by downstream processes, preventing unauthorized PHI or other sensitive information from being exposed | P0 | Phase 1 | AI Output PHI Scanner | User Story | New | Pending | Extraction & OCR | AI Output Protection | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Application Security
CIP-APPSEC-010 | CIP-PA-320 | The CIP platform shall implement : AI output length gate — hallucinated output suppressed if exceeds MAX_CARD_LENGTH per card type. CIP shall validate AI-generated outputs against capability-specific output contracts, including required structure, permitted values, content-length constraints, evidence requirements, and applicable safety and data-protection rules before the output is presented or used by downstream workflows. | P0 | Phase 1 | AI Output Length Gate | User Story | New | Pending | Extraction & OCR | AI Output Controls | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Application Security
CIP-APPSEC-008 | CIP-PA-328 | The CIP platform shall implement : PostgreSQL GRANT per service role — each service has database role with only the table permissions it requires. CIP shall enforce least-privilege database access controls, ensuring each application service has only the minimum permissions required to perform its authorized functions | P0 | Phase 1 | PostgreSQL GRANT per Service Role | User Story | New | Pending | Data & Persistence | Database Access Controls | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Application Security
CIP-APPSEC-005 | CIP-PA-332 | The CIP platform shall implement : ACCOUNT_MANAGER managed_clients validation — can only query clients in their managed_clients JWT claim. CIP shall restrict Account Manager access to the clients explicitly assigned to their authorized portfolio and shall validate the requested client scope server-side before permitting access to cross-client data, analytics, reports, or exports. | P0 | Phase 1 | ACCOUNT_MANAGER Managed_clients Validation | User Story | New | Pending | Analytics, Dashboard & Reporting | Application Security Controls | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Application Security
CIP-APPSEC-010 | CIP-PA-335 | The CIP platform shall implement : Portal session anomaly detection — processor accessing unusual volume or outside normal domain triggers security alert. CIP shall monitor access to sensitive data and privileged resources for anomalous or potentially unauthorized behavior, considering factors such as role, client and workflow scope, data sensitivity, access volume, access patterns, and applicable historical or expected behavior, and shall generate security alerts when defined risk thresholds are met | P0 | Phase 1 | Portal Session Anomaly Detection | User Story | New | Pending | Extraction & OCR | Session Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Application Security
CIP-DEPA-006 | CIP-PA-340 | The CIP platform shall implement : Clinical indication extraction — BioBERT/suitable LLM extraction of diagnosis concepts, severity, prior treatment from PA narrative. CIP shall support Clinical indication extraction, including BioBERT extraction of diagnosis concepts, severity, prior treatment from PA narrative, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | Clinical Indication Extraction | User Story | New | Pending | Extraction & OCR | Clinical Indication Extraction | Data Extraction -- Prior Auth | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Extraction -- Prior Auth
CIP-DEPA-003 | CIP-PA-343 | The CIP platform shall implement : Chain of Thought criteria evaluation — step-by-step reasoning per criterion before verdict, not binary single-pass classification. CIP shall support Chain of Thought criteria evaluation, including step-by-step reasoning per criterion before verdict, not binary single-pass classification, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | Chain of Thought Criteria Evaluation | User Story | New | Pending | Classification | PA Criteria Evaluation | Data Extraction -- Prior Auth | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Extraction -- Prior Auth
CIP-DEPA-009 | CIP-PA-345 | The CIP platform shall implement : Age and sex appropriateness rules — procedure approvals restricted by member demographics per CMS policy. CIP shall support Age and sex appropriateness rules, including procedure approvals restricted by member demographics per CMS policy, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | Age and Sex Appropriateness Rules | User Story | New | Pending | Security, Privacy & Access | Clinical Appropriateness Validation | Data Extraction -- Prior Auth | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Extraction -- Prior Auth
CIP-DEPA-008 | CIP-PA-347 | The CIP platform shall implement : Peer-to-peer review eligibility rules — availability after denial, scheduling window, P2P outcome documentation. | P1 | Phase 1 | Peer-to-peer Review Eligibility Rules | User Story | New | Pending | Reliability, Performance & Operations | Peer-to-Peer Review Rules | Data Extraction -- Prior Auth | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Extraction -- Prior Auth
CIP-PA-004 | CIP-PA-352 | The CIP platform shall implement : PRECEDENT vector search — de-identified historical case similarity search against vector store in as_db. CIP shall provide authorized similar-case intelligence that identifies relevant historical cases using governed clinical and operational characteristics, while protecting member and client confidentiality and clearly distinguishing historical case information from authoritative clinical guidelines, policies, and current-case evidence. | P0 | Phase 1 | PRECEDENT Vector Search | User Story | New | Pending | Guideline & Policy Resolution | Platform Architecture | Platform Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Platform Arch
CIP-PA-004 | CIP-PA-353 | The CIP platform shall implement : PRECEDENT vector store indexing — de-identified case records indexed by CPT code, payer, Prior Authorization document type, outcome. CIP shall maintain a governed searchable representation of authorized historical cases using relevant clinical, request, evidence, guideline, quality, and outcome attributes to support Similar Case Intelligence while protecting member and client confidentiality | P0 | Phase 1 | PRECEDENT Vector Store Indexing | User Story | New | Pending | Guideline & Policy Resolution | Platform Architecture | Platform Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Platform Arch
CIP-PA-003 | CIP-PA-357 | The CIP platform shall implement the following requirement: to (Release 1.1/1.2): Session history de-identification for within-session memory [RELEASE 1.1] — codes and field names only, no patient identifiers. | P0 | Phase 1 | To (Release 1.1/1.2): Session History De-identification for Within-session Memory [RELEASE 1.1] | User Story | New | Pending | Core Platform Capabilities | Platform Architecture | Platform Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Platform Arch
CIP-AIRF-004 | CIP-PA-359 | The CIP platform shall implement : Chain of Thought adverse letter drafting — Step 1 reasoning chain for clinical rationale, Step 2 generates letter from reasoning. | P1 | Phase 1 | Chain of Thought Adverse Letter Drafting | User Story | New | Pending | Communication & Delivery | AI-Assisted Communication | AI Reasoning Framework | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | AI Reasoning Framework
CIP-AIRF-004 | CIP-PA-362 | The CIP platform shall implement : Reflection revision loop — if issues found in reflection step, one revision pass before presenting letter to processor. | P1 | Phase 1 | Reflection Revision Loop | User Story | New | Pending | Communication & Delivery | AI-Assisted Communication | AI Reasoning Framework | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | AI Reasoning Framework
CIP-AIRF-006 | CIP-PA-364 | The CIP platform shall implement : Structured output enforcement — CoPilot cards return validated JSON schema, retry on schema validation failure. | P1 | Phase 1 | Structured Output Enforcement | User Story | New | Pending | Data & Persistence | AI Output & Reasoning Controls | AI Reasoning Framework | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | AI Reasoning Framework
CIP-AIRF-008 | CIP-PA-367 | The CIP platform shall implement the following requirement: to (Release 1.1/1.2): Full guideline corpus RAG [RELEASE 1.1] — complete InterQual and MCG corpus search for ambiguous PA cases. | P1 | Phase 1 | To (Release 1.1/1.2): Full Guideline Corpus RAG [RELEASE 1.1] | User Story | New | Pending | Guideline & Policy Resolution | Guideline Retrieval & Reasoning | AI Reasoning Framework | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | AI Reasoning Framework
CIP-PACG-008 | CIP-PA-372 | The CIP platform shall implement the following requirement: provider license/validity, network participation and specialty validated against authoritative sources. Expected outcome: provider-related exceptions are identified before decisioning. | P1 | Phase 1 | Provider License/validity, Network Participation and Specialty Validated Against Authoritative Sources | User Story | New | Pending | Core Platform Capabilities | Prior Authorization Capabilities | PA Capability Gap | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | PA Capability Gap
CIP-PACG-007 | CIP-PA-378 | The CIP platform shall implement the following requirement: an integrated document viewer with page navigation, search, jump-to-page and region-of-interest highlighting. Expected outcome: I can validate each extracted value against the source document. The Chart one the right, the extracted fields on the left. From the extracted fields should be able to point to the section on the chart. | P1 | Phase 1 | An Integrated Document Viewer with Page Navigation, Search, Jump-to-page and Region-of-interest Highlighting | User Story | New | Pending | Extraction & OCR | Prior Authorization Capabilities | PA Capability Gap | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | PA Capability Gap
CIP-PACG-002 | CIP-PA-382 | The CIP platform shall implement the following requirement: 30-day license-expiry reports and clinician/team-lead alerts. Expected outcome: expiring credentials are addressed before they affect eligibility. | P1 | Phase 1 | 30-day License-expiry Reports and Clinician/team-lead Alerts | User Story | New | Pending | Analytics, Dashboard & Reporting | Prior Authorization Capabilities | PA Capability Gap | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | PA Capability Gap
CIP-PACG-012 | CIP-PA-385 | The CIP platform shall implement the following requirement: configurable rules to determine whether authorization is required. Expected outcome: no-auth-required cases are communicated and closed while required cases continue through authorization processing. | P1 | Phase 1 | Configurable Rules to Determine Whether Authorization Is Required | User Story | New | Pending | Security, Privacy & Access | Prior Authorization Capabilities | PA Capability Gap | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | PA Capability Gap
CIP-PACG-012 | CIP-PA-386 | The CIP platform shall implement the following requirement: to look up existing authorizations and create or update the appropriate authorization record. Expected outcome: duplicate cases are avoided and the correct authorization lifecycle is maintained. | P1 | Phase 1 | To Look Up Existing Authorizations and Create or Update the Appropriate Authorization Record | User Story | New | Pending | Security, Privacy & Access | Prior Authorization Capabilities | PA Capability Gap | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | PA Capability Gap
CIP-PACG-008 | CIP-PA-389 | The CIP platform shall implement the following requirement: automated reconciliation between CIP and the downstream case-management solution. Expected outcome: missing, failed or mismatched PA cases/documents are identified and resolved. | P3 | Phase 1 | Automated Reconciliation Between CIP and the Downstream Case-management Solution | User Story | New | Pending | Core Platform Capabilities | Prior Authorization Capabilities | PA Capability Gap | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | PA Capability Gap
CIP-CG-005 | CIP-PA-400 | The CIP platform shall implement : UHDDS principal diagnosis definition enforcement — inpatient coding and UB-04 document types. CIP shall support UHDDS principal diagnosis definition enforcement, including inpatient coding and UB-04 document types, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | UHDDS Principal Diagnosis Definition Enforcement | User Story | New | Pending | Classification | Clinical Rule Validation | Clinical Guidelines Validation | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Clinical guidelines
CIP-CG-012 | CIP-PA-402 | The CIP platform shall implement : OASIS-E1 skip pattern enforcement — conditional item logic per assessment type SOC, Recert, Discharge. | P3 | Phase 1 | OASIS-E1 Skip Pattern Enforcement | User Story | New | Pending | Core Platform Capabilities | Clinical Rule Validation | Clinical Guidelines Validation | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Clinical guidelines
CIP-CG-015 | CIP-PA-405 | The CIP platform shall implement : CDI query and response storage — cdi.queried Kafka event, response capture, DRG impact assessment. CIP shall support CDI query and response storage, including cdi.queried Kafka event, response capture, DRG impact assessment, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | CDI Query and Response Storage | User Story | New | Pending | Workflow & Event Orchestration | Clinical Documentation Workflow | Clinical Guidelines Validation | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Clinical guidelines
CIP-F-001 | CIP-PA-411 | 0 | P1 | Phase 1 | 0 | User Story | New | Pending | Core Platform Capabilities | Functional / Existing | Functional / Existing | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Functional / Existing
CIP-CIOS-011 | CIP-PA-412 | The CIP platform shall implement : ICD_VALID card — CMS ICD-10-CM code table lookup, validity, maximum specificity check, HCC mapping status. CIP shall support ICD_VALID card, including CMS ICD-10-CM code table lookup, validity, maximum specificity check, HCC mapping status, using governed and configurable controls with appropriate validation, traceability, security, and exception handling for the applicable workflow. | P1 | Phase 1 | ICD_VALID Card | User Story | New | Pending | Data & Persistence | ICD Validation | CIOS | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | CIOS
CIP-CIOS-012 | CIP-PA-416 | The CIP platform shall implement : Inpatient Coding document-type-specific cards — PRINCIPAL_DX_ADVISOR, CC_MCC_OPPORTUNITY, CDI_QUERY_STATUS. | P3 | Phase 1 | Inpatient Coding Document-type-specific Cards | User Story | New | Pending | Domain Workflow | Inpatient Coding Workflow | CIOS | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | CIOS
CIP-CIOS-012 | CIP-PA-417 | The CIP platform shall implement : Outpatient Coding document-type-specific cards — APC_ADVISOR, OCE_CHECKER, MODIFIER_ADVISORY. | P3 | Phase 1 | Outpatient Coding Document-type-specific Cards | User Story | New | Pending | Domain Workflow | Outpatient Coding Workflow | CIOS | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | CIOS
CIP-CIOS-012 | CIP-PA-419 | The CIP platform shall implement : Risk Adjustment document-type-specific cards — HCC_MAPPING, RAF_DELTA, SUSPECT_ADVISOR, FACE_TO_FACE_CHECK. | P3 | Phase 1 | Risk Adjustment Document-type-specific Cards | User Story | New | Pending | Domain Workflow | Risk Adjustment Workflow | CIOS | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | CIOS
CIP-CIOS-014 | CIP-PA-422 | The CIP platform shall implement : Care gap checklist — addressed / outstanding / declined status per gap with care manager input. | P3 | Phase 1 | Care Gap Checklist | User Story | New | Pending | Core Platform Capabilities | Care Gap Management | CIOS | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | CIOS
CIP-DSEC-007 | CIP-PA-438 | The CIP platform shall implement : 8-role RBAC model — PROCESSOR, QA_AUDITOR, SUPERVISOR, CLIENT_VIEWER, ACCOUNT_MANAGER, ADMIN, CARE_MANAGER, PHARMACIST. CIP shall provide a governed role- and permission-based authorization framework that enforces least-privilege access across clinical, quality, operational, client-facing, and administrative functions, with access further constrained by applicable client scope, workflow context, data classification, qualifications, and resource-level authorization. | P0 | Phase 1 | 8-role RBAC Model | User Story | New | Pending | Security, Privacy & Access | Identity & Access Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Security
CIP-INF-013 | CIP-PA-443 | The CIP platform shall implement : RA batch trigger and scheduling — CMS submission deadline or plan-initiated. | P2 | Phase 1 | RA Batch Trigger and Scheduling | User Story | New | Pending | Intake & Ingestion | Platform Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Batch
CIP-INF-013 | CIP-PA-445 | The CIP platform shall implement : RAPS or EDPS submission file generation and CMS submission. | P2 | Phase 1 | RAPS or EDPS Submission File Generation and CMS Submission | User Story | New | Pending | Intake & Ingestion | Platform Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Batch
CIP-INF-018 | CIP-PA-446 | The CIP platform shall implement : ra.batch.submitted Kafka event and receipt logging. | P2 | Phase 1 | Ra.batch.submitted Kafka Event and Receipt Logging | User Story | New | Pending | Workflow & Event Orchestration | Event Infrastructure | Infrastructure | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Batch
CIP-APPSEC-011 | CIP-PA-448 | The CIP platform shall implement : Warm transfer sentinel phrase detection — distress, clinical question, member request, safety concern triggers transfer.requested. | P2 | Phase 1 | Warm Transfer Sentinel Phrase Detection | User Story | New | Pending | Core Platform Capabilities | Conversation Safety Controls | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Application Security
CIP-PA-002 | CIP-PA-605 | The CIP platform shall implement : Cross-session care management summary storage — post-session structured summary written to cm_session_summaries in wip_db. | P3 | Phase 1 | Cross-session Care Management Summary Storage | User Story | New | Pending | Domain Workflow | Platform Architecture | Platform Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Platform Arch
CIP-PA-006 | CIP-PA-606 | The CIP platform shall implement : Session summary de-identification — summaries contain gap IDs, barrier categories, sentiment scores, never clinical narrative PHI. | P3 | Phase 1 | Session Summary De-identification | User Story | New | Pending | Security, Privacy & Access | Platform Architecture | Platform Architecture | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Platform Arch
CIP-P-001 | CIP-PA-626 | The CIP platform shall implement the following requirement: transaction-processing performance targets defined and enforced. Expected outcome: prior authorization work completes within agreed operational SLAs. CIP shall define, monitor, and enforce performance and processing-time objectives for critical platform services and workflows, ensuring technology components operate within established service-level objectives and do not introduce avoidable delays into clinical and operational processing. CIP shall support achievement of agreed Prior Authorization service levels by identifying and mitigating avoidable technology and workflow delays and providing timely visibility into transactions at risk of missing applicable obligations | P0 | Phase 1 | Transaction-processing Performance Targets Defined and Enforced | User Story | New | Pending | Reliability, Performance & Operations | Performance | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Performance
CIP-AVA-001 | CIP-PA-628 | The CIP platform shall implement the following requirement: platform availability targets and service dependencies defined. Expected outcome: critical workflows remain available. CIP shall define and maintain availability, resilience, recovery, and dependency requirements for critical clinical and operational workflows, ensuring essential services meet established availability objectives and that dependency failures do not unnecessarily disrupt unaffected platform capabilities | P0 | Phase 1 | Platform Availability Targets and Service Dependencies Defined | User Story | New | Pending | Reliability, Performance & Operations | Availability | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Availability
CIP-R-001 | CIP-PA-629 | The CIP platform shall implement the following requirement: failed transactions to recover safely. Expected outcome: no authorization case is lost or duplicated. CIP shall provide resilient transaction processing and recovery controls that preserve the integrity, identity, state, and history of authorization cases through technical and workflow failures, ensuring accepted transactions are not lost and repeated processing does not create duplicate business outcomes | P0 | Phase 1 | Failed Transactions to Recover Safely | User Story | New | Pending | Reliability, Performance & Operations | Resilience | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Resilience
CIP-DIS-001 | CIP-PA-630 | The CIP platform shall implement the following requirement: RTO/RPO targets and tested recovery procedures. Expected outcome: service can be restored after a major outage. CIP shall define and maintain risk- and business-criticality-based Recovery Time Objectives (RTO) and Recovery Point Objectives (RPO) for critical platform capabilities and authoritative data, with recovery architectures and procedures designed to meet the applicable objectives following a major service disruption or disaster | P0 | Phase 1 | RTO/RPO Targets and Tested Recovery Procedures | User Story | New | Pending | Reliability, Performance & Operations | Disaster Recovery | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Disaster Recovery
CIP-UA-001 | CIP-PA-631 | The CIP platform shall implement the following requirement: consistent and accessible workflows. Expected outcome: clinical and operational tasks can be completed efficiently. CIP shall provide consistent, intuitive, role-appropriate, and accessible user experiences across clinical and operational workflows, using standardized interaction patterns and contextual workflow guidance to enable users to complete authorized tasks efficiently, accurately, and safely | P0 | Phase 1 | Consistent and Accessible Workflows | User Story | New | Pending | Workflow & Event Orchestration | Usability & Accessibility | Usability & Accessibility | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Usability & Accessibility
CIP-O-001 | CIP-PA-632 | The CIP platform shall implement the following requirement: As support staff, I need end-to-end telemetry so that failures and performance degradation can be detected and diagnosed. CIP shall provide end-to-end observability across infrastructure, application services, databases, integrations, event processing, AI services, and critical business workflows, enabling authorized support teams to detect, correlate, diagnose, and respond to failures and performance degradation CIP shall correlate operational telemetry across services, transactions, events, workflows, AI executions, and external dependencies to enable support teams to determine the source, scope, business impact, and affected workflows of operational issues | P0 | Phase 1 | end to end telemetry tracking | User Story | New | Pending | Workflow & Event Orchestration | Observability | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Observability
CIP-M-001 | CIP-PA-633 | The CIP platform shall implement the following requirement: modular, versioned and supportable services. Expected outcome: changes can be deployed safely. CIP shall provide a modular and maintainable platform architecture with clearly defined capability boundaries, governed interfaces, versioned software and configuration artifacts, and independently manageable components, enabling platform capabilities to evolve with minimal unintended impact on other services and workflows. | P0 | Phase 1 | Modular, Versioned and Supportable Services | User Story | New | Pending | Configuration & Administration | Maintainability | Maintainability | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Maintainability
CIP-CM-001 | CIP-PA-635 | The CIP platform shall implement the following requirement: capacity thresholds and forecasts. Expected outcome: infrastructure is scaled before demand causes service degradation. CIP shall monitor and forecast capacity requirements across critical platform resources and workloads using current utilization, processing demand, historical trends, expected business growth, and defined service-level objectives, enabling capacity to be adjusted before resource constraints cause material service degradation | P0 | Phase 1 | Capacity Thresholds and Forecasts | User Story | New | Pending | Reliability, Performance & Operations | Capacity Management | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Capacity Management
CIP-HIPAA-001 | CIP-PA-636 | The CIP platform shall implement the following requirement: PHI handled in accordance with applicable HIPAA/HITECH obligations. Expected outcome: confidentiality, integrity and availability are protected. CIP shall protect PHI and other sensitive health information throughout its lifecycle using risk-based administrative and technical controls designed to support applicable HIPAA, HITECH, contractual, and organizational privacy and security obligations, including controls for confidentiality, integrity, availability, access, use, disclosure, retention, and disposition. | P0 | Phase 1 | PHI Handled in Accordance with Applicable HIPAA/HITECH Obligations | User Story | New | Pending | Security, Privacy & Access | HIPAA / HITECH | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | HIPAA / HITECH
CIP-IA-001 | CIP-PA-642 | The CIP platform shall implement the following requirement: centralized identity, RBAC and least privilege. Expected outcome: only authorized users and services can access capabilities and data. CIP shall provide centralized identity and authorization governance for human users and application services, enforcing role- and permission-based access, least privilege, and contextual access controls across platform capabilities, data, integrations, and administrative functions | P0 | Phase 1 | Centralized Identity, RBAC and Least Privilege | User Story | New | Pending | API & Integration | Identity & Access | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Identity & Access
CIP-EKM-001 | CIP-PA-643 | The CIP platform shall implement the following requirement: sensitive data encrypted with managed keys. Expected outcome: data is protected at rest and in transit. CIP shall protect PHI and other sensitive information using approved cryptographic controls for data at rest and in transit, with the required level of protection determined by applicable data classification, security, privacy, regulatory, and contractual requirements. | P0 | Phase 1 | Sensitive Data Encrypted with Managed Keys | User Story | New | Pending | Security, Privacy & Access | Encryption & Key Management | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Encryption & Key Management
CIP-SS-001 | CIP-PA-645 | The CIP platform shall implement the following requirement: automated security controls in CI/CD. Expected outcome: vulnerable code and dependencies are blocked before release. CIP shall integrate automated security and software-supply-chain controls throughout the software delivery lifecycle to identify vulnerabilities, insecure configurations, exposed secrets, vulnerable dependencies, and other material security risks before changes are promoted to production | P0 | Phase 1 | Automated Security Controls in CI/CD | User Story | New | Pending | Security, Privacy & Access | Secure SDLC | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Secure SDLC
CIP-AIPS-001 | CIP-PA-648 | The CIP platform shall implement the following requirement: defenses against prompt injection, data exfiltration and unsafe tool use. Expected outcome: AI cannot bypass system controls. CIP shall perform risk-based threat modeling for material platform capabilities, AI-enabled workflows, data flows, and internal and external integrations to identify security, privacy, tenant-isolation, AI, clinical-integrity, and operational threats and define appropriate controls before production use. | P0 | Phase 1 | Defenses Against Prompt Injection, Data Exfiltration and Unsafe Tool Use | User Story | New | Pending | Security, Privacy & Access | AI / Prompt Security | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | AI / Prompt Security
CIP-SMIR-001 | CIP-PA-650 | The CIP platform shall implement the following requirement: security telemetry and incident playbooks. Expected outcome: suspicious behavior can be detected and contained. CIP shall generate and correlate security-relevant telemetry across identities, data access, applications, APIs, services, integrations, tenant boundaries, privileged operations, and AI-enabled capabilities to support timely detection and investigation of suspicious or unauthorized activity | P0 | Phase 1 | Security Telemetry and Incident Playbooks | User Story | New | Pending | API & Integration | Security Monitoring & Incident Response | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Security Monitoring & Incident Response
CIP-DUL-001 | CIP-PA-652 | The CIP platform shall implement the following requirement: data use restricted to approved purposes. Expected outcome: client/PHI data is not repurposed without authorization. CIP shall restrict the use of client, PHI, and other sensitive information to authorized purposes consistent with applicable client agreements, privacy requirements, data-use policies, and organizational governance, preventing data from being repurposed for unrelated or secondary uses without appropriate authorization. | P0 | Phase 1 | Data Use Restricted to Approved Purposes | User Story | New | Pending | Security, Privacy & Access | Data Use Limitation | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Use Limitation
CIP-OWN-001 | CIP-PA-655 | The CIP platform shall implement the following requirement: named owners and stewards for critical data domains. Expected outcome: accountability is clear. CIP shall maintain defined ownership and stewardship for critical clinical, operational, configuration, AI, and analytical data domains, ensuring accountability for data definitions, classification, quality, authorized use, governance, and lifecycle management. | P0 | Phase 1 | Named Owners and Stewards for Critical Data Domains | User Story | New | Pending | Classification | Ownership & Stewardship | Ownership & Stewardship | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Ownership & Stewardship
CIP-DC-001 | CIP-PA-656 | The CIP platform shall implement the following requirement: data classified by sensitivity and purpose. Expected outcome: controls are applied consistently. CIP shall classify clinical, operational, client, security, AI, analytical, and other information according to governed sensitivity classifications and authorized-use purposes, enabling appropriate privacy, security, access, processing, disclosure, retention, and monitoring controls to be applied consistently. | P0 | Phase 1 | Data Classified By Sensitivity and Purpose | User Story | New | Pending | Security, Privacy & Access | Data Classification | Data Classification | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Classification
CIP-DQ-001 | CIP-PA-658 | The CIP platform shall implement the following requirement: measurable data-quality controls. Expected outcome: downstream clinical and operational decisions use reliable information. CIP shall implement measurable and risk-based data-quality controls across critical clinical, operational, configuration, AI-derived, and analytical information to assess and maintain the completeness, accuracy, validity, consistency, timeliness, integrity, and traceability required for its intended use. | P0 | Phase 1 | Measurable Data-quality Controls | User Story | New | Pending | Configuration & Administration | Data Quality | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Quality
CIP-DRS-001 | CIP-PA-662 | The CIP platform shall implement the following requirement: residency and segregation requirements enforced. Expected outcome: data remains in approved locations and boundaries. CIP shall enforce applicable data residency, processing-location, and tenant/client segregation requirements across the storage, processing, transmission, replication, backup, analytics, AI, integration, and other handling of sensitive information, ensuring data remains within approved geographic, organizational, and security boundaries | P0 | Phase 1 | Residency and Segregation Requirements Enforced | User Story | New | Pending | Security, Privacy & Access | Data Residency & Segregation | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Data Residency & Segregation
CIP-CR-001 | CIP-PA-669 | The CIP platform shall implement the following requirement: revalidation triggered by material changes. Expected outcome: prior approvals remain valid. | P2 | Phase 1 | Revalidation Triggered By Material Changes | User Story | New | Pending | Model / AI Governance | Change & Revalidation | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Change & Revalidation
CIP-RET-001 | CIP-PA-690 | The CIP platform shall implement the following requirement: the platform requirements for retry & resubmission to be explicitly defined and supported. Expected outcome: retry rules, retry frequency, maximum attempts and manual resubmission process for failed output/api transactions is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Retry & Resubmission to Be Explicitly Defined and Supported | User Story | New | Pending | Workflow & Event Orchestration | Retry & Resubmission | Retry & Resubmission | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Retry & Resubmission
CIP-BA-001 | CIP-PA-720 | The CIP platform shall implement the following requirement: the platform requirements for business availability to be explicitly defined and supported. Expected outcome: solution shall meet the agreed availability target during required operating periods is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Business Availability to Be Explicitly Defined and Supported | User Story | New | Pending | Reliability, Performance & Operations | Business availability | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Business availability
CIP-CSA-001 | CIP-PA-721 | The CIP platform shall implement the following requirement: the platform requirements for critical service availability to be explicitly defined and supported. Expected outcome: critical pa services shall meet separately agreed availability targets where applicable is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Critical Service Availability to Be Explicitly Defined and Supported | User Story | New | Pending | Reliability, Performance & Operations | Critical service availability | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Critical service availability
CIP-RS-001 | CIP-PA-725 | The CIP platform shall implement the following requirement: the platform requirements for retry strategy to be explicitly defined and supported. Expected outcome: transient failures shall be retried using approved configurable policies is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Retry Strategy to Be Explicitly Defined and Supported | User Story | New | Pending | Configuration & Administration | Retry strategy | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Retry strategy
CIP-DLH-001 | CIP-PA-726 | The CIP platform shall implement the following requirement: the platform requirements for dead-letter handling to be explicitly defined and supported. Expected outcome: transactions that fail after retry shall remain in a recoverable exception state is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Dead-letter Handling to Be Explicitly Defined and Supported | User Story | New | Pending | Workflow & Event Orchestration | Dead-letter handling | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Dead-letter handling
CIP-I-001 | CIP-PA-727 | The CIP platform shall implement the following requirement: the platform requirements for idempotency to be explicitly defined and supported. Expected outcome: repeated transactions shall not create unintended duplicate cases, documents or communications is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Idempotency to Be Explicitly Defined and Supported | User Story | New | Pending | Communication & Delivery | Idempotency | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Idempotency
CIP-AUT-001 | CIP-PA-738 | The CIP platform shall implement the following requirement: the platform requirements for authentication to be explicitly defined and supported. Expected outcome: interfaces shall use organization-approved authentication mechanisms is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Authentication to Be Explicitly Defined and Supported | User Story | New | Pending | Security, Privacy & Access | Authentication | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Authentication
CIP-AUTH-001 | CIP-PA-739 | The CIP platform shall implement the following requirement: the platform requirements for authorization to be explicitly defined and supported. Expected outcome: access shall follow least-privilege, role-based authorization is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Authorization to Be Explicitly Defined and Supported | User Story | New | Pending | Security, Privacy & Access | Authorization | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Authorization
CIP-ET-001 | CIP-PA-740 | The CIP platform shall implement the following requirement: the platform requirements for encryption in transit to be explicitly defined and supported. Expected outcome: sensitive data shall be encrypted in transit using approved protocols is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Encryption in Transit to Be Explicitly Defined and Supported | User Story | New | Pending | Security, Privacy & Access | Encryption in transit | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Encryption in transit
CIP-EAR-001 | CIP-PA-741 | The CIP platform shall implement the following requirement: the platform requirements for encryption at rest to be explicitly defined and supported. Expected outcome: sensitive data and documents shall be encrypted at rest using approved standards is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Encryption at Rest to Be Explicitly Defined and Supported | User Story | New | Pending | Security, Privacy & Access | Encryption at rest | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Encryption at rest
CIP-RDC-001 | CIP-PA-761 | The CIP platform shall implement the following requirement: the platform requirements for reference data consistency to be explicitly defined and supported. Expected outcome: codes, statuses and reference values shall be consistent across integrated systems is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Reference Data Consistency to Be Explicitly Defined and Supported | User Story | New | Pending | Data & Persistence | Reference data consistency | Reference data consistency | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Reference data consistency
CIP-DELI-001 | CIP-PA-771 | The CIP platform shall implement the following requirement: the platform requirements for delivery retry to be explicitly defined and supported. Expected outcome: failed communications shall follow approved retry and alternate/manual handling is consistently handled for Prior Authorization. | P1 | Phase 1 | The Platform Requirements for Delivery Retry to Be Explicitly Defined and Supported | User Story | New | Pending | Communication & Delivery | Delivery retry | Platform / Cross-cutting | Clinical Desktop, CIP Connected, CIP Integrated, CIP Agentic | Delivery retry